## Plan
2019-11-04 | 2019-11-05 | 2019-11-06 | 2019-11-07 | 2019-11-08 | 2019-11-09 | 2019-11-10 | 2019-11-11 | 2019-11-12 | 2019-11-13 | 2019-11-14
[5 empty] | S A T U R D A Y | S U N D A Y
Github | PyQt5 | Logging |  |  |  |  | PyInstaller/fbs | Code Review | Code Review | Presentation
Create Folder Structure | PyTest | SQLAlcchemy | [5 empty] | Unit Testing | Integration Test
Checkin Empty files view.py controller.py model.py | Discuss about naming conventions
Download Postgresql | Add appropriate methods/functions Add definitions to the functions

## Plan_Execution_Update
2019-11-04 | 2019-11-05 | 2019-11-06 | 2019-11-07 | 2019-11-08 | 2019-11-09 | 2019-11-10 | 2019-11-11 | 2019-11-12 | 2019-11-13 | 2019-11-14
[5 empty] | S A T U R D A Y | S U N D A Y
Github | PyQt5 | Logging |  |  |  |  | PyInstaller/fbs | Code Review | Code Review | Presentation
Create Folder Structure | PyTest | SQLAlcchemy | [5 empty] | Unit Testing | Integration Test
Checkin Empty files view.py controller.py model.py | Discuss about naming conventions
Download Postgresql | Add appropriate methods/functions Add definitions to the functions

## Things to Remember
Things to remember
Static Variables
DEBUG_MODE/Logging:
{LoginID:Password}:Dictionary
COLUMNS_LIST:List

## AdditionsToPlan
Sl No. | Additions to the initial plan
1 | To have a logout button on screen at all point of time after once the user logs in
2 | Action after a CSV content has been updated to DB : Provide options Logout ¦ Update Again
3

## Aditya
2019-11-04 | 2019-11-05 | 2019-11-06 | 2019-11-07 | 2019-11-08 | 2019-11-09 | 2019-11-10 | 2019-11-11 | 2019-11-12 | 2019-11-13 | 2019-11-14
[5 empty] | S A T U R D A Y | S U N D A Y
Learnt command prompt GIT commands
Created Folder Structure & Checked in files to Github
Downlaoded Postgresql
Added User Stories on Github

## Suvarna
2019-11-04 | 2019-11-05 | 2019-11-06 | 2019-11-07 | 2019-11-08 | 2019-11-09 | 2019-11-10 | 2019-11-11 | 2019-11-12 | 2019-11-13 | 2019-11-14
[5 empty] | S A T U R D A Y | S U N D A Y
Guided on command prompt GIT commands
Guided on Downlaoding Postgresql
Downlaoded Postgresql

## Sanju
2019-11-04 | 2019-11-05 | 2019-11-06 | 2019-11-07 | 2019-11-08 | 2019-11-09 | 2019-11-10 | 2019-11-11 | 2019-11-12 | 2019-11-13 | 2019-11-14
[5 empty] | S A T U R D A Y | S U N D A Y
Learnt command prompt GIT commands
Downlaoded Postgresql

## Tamdin
2019-11-04 | 2019-11-05 | 2019-11-06 | 2019-11-07 | 2019-11-08 | 2019-11-09 | 2019-11-10 | 2019-11-11 | 2019-11-12 | 2019-11-13 | 2019-11-14
[5 empty] | S A T U R D A Y | S U N D A Y
Learnt command prompt GIT commands
Downlaoded Postgresql