## Plan
2019-11-04 | 2019-11-05 | 2019-11-06 | 2019-11-07 | 2019-11-08 | 2019-11-09 | 2019-11-10 | 2019-11-11 | 2019-11-12 | 2019-11-13 | 2019-11-14
[5 empty] | S A T U R D A Y | S U N D A Y
Github | PyQt5 | Logging | Add User Stories | Add User Stories |  |  | PyInstaller/fbs | Code Review | Code Review | Presentation
Create Folder Structure | PyTest | SQLAlcchemy | SQLAlcchemy | DB Setup to be done by all |  |  | Code View.py to show/hide buttons dinamically | Unit Testing | Integration Test
Checkin Empty files view.py controller.py model.py | Discuss about naming conventions |  | Code View.py for Login | Code View.py for browsing file |  |  | Code test_controller.py for login validation | Beautify the frontend | Review Documentation
Download Postgresql | Add appropriate methods/functions Add doc strings to the functions |  | Code Controller.py for Login | Code Controller.py for csv validation |  |  | Code test_controller.py for csv validation | Any Additional functionalities to be added | Work on Presentation files
|  |  | Code Controller.py for implementing Logging | Code Controller.py for updating db with csv data |  |  | Code test_controller.py for send_csv | Implement Logout functionality | Test Packaging
[7 empty] | Research Packaging | Packaging to be done

## Plan_Execution_Update
2019-11-04 | 2019-11-05 | 2019-11-06 | 2019-11-07 | 2019-11-08 | 2019-11-09 | 2019-11-10 | 2019-11-11 | 2019-11-12 | 2019-11-13 | 2019-11-14
[5 empty] | S A T U R D A Y | S U N D A Y
Github | PyQt5 | Logging | Add User Stories | Add User Stories |  |  | PyInstaller/fbs | Code Review | Code Review | Presentation
Create Folder Structure | PyTest | SQLAlcchemy | SQLAlcchemy | DB Setup to be done by all |  |  | Code View.py to show/hide buttons dinamically | Unit Testing | Integration Test
Checkin Empty files view.py controller.py model.py | Discuss about naming conventions | Discuss about naming conventions | Code View.py for Login | Code View.py for browsing file |  |  | Code test_controller.py for login validation | Beautify the frontend | Review Documentation
Download Postgresql | Add appropriate methods/functions Add definitions to the functions | Add appropriate methods/functions Add doc strings to the functions | Code Controller.py for Login | Code Controller.py for csv validation |  |  | Code test_controller.py for csv validation | Any Additional functionalities to be added | Work on Presentation files
|  |  | Code Controller.py for implementing Logging | Code Controller.py for updating db with csv data |  |  | Code test_controller.py for send_csv | Implement Logout functionality | Test Packaging
[7 empty] | Research Packaging | Packaging to be done

## Things to Remember
Things to remember
Static Variables
DEBUG_MODE/Logging:
{LoginID:Password}:Dictionary
COLUMNS_LIST:List
DB path

## AdditionsToPlan
Sl No. | Additions to the initial plan
1 | To have a logout button on screen at all point of time after once the user logs in
2 | Action after a CSV content has been updated to DB : Provide options Logout ¦ Update Again
3

## Aditya
2019-11-04 | 2019-11-05 | 2019-11-06 | 2019-11-07 | 2019-11-08 | 2019-11-09 | 2019-11-10 | 2019-11-11 | 2019-11-12 | 2019-11-13 | 2019-11-14
[5 empty] | S A T U R D A Y | S U N D A Y
Learnt command prompt GIT commands
Created Folder Structure & Checked in files to Github
Downlaoded Postgresql
Added User Stories on Github

## Suvarna
2019-11-04 | 2019-11-05 | 2019-11-06 | 2019-11-07 | 2019-11-08 | 2019-11-09 | 2019-11-10 | 2019-11-11 | 2019-11-12 | 2019-11-13 | 2019-11-14
[5 empty] | S A T U R D A Y | S U N D A Y
Guided on command prompt GIT commands | Learnt PyQt5 Calculator App | Took a session on Logging in Python | Research SQLAlchemy PostgreSQL | Research & shared knowledge for setting a new DB user account which could be used as a common one for project
Guided on Downlaoding Postgresql | Learnt pytest & unittest (Python Unit test) | Added LearningModule folder with tutorial files for Logging in Python and a quick guide for GIT commands | Shared Knowledge - SQLAlchemy - PostgreSQL - pgAdmin GUI | Coded model.py
Downlaoded Postgresql | Created & Added this Project plan file to repository | Added function definitions, doc strings & to-dos for the controller & model files |  | Coded send_csv() in controller.py
Research PyQt5 | Added the test folder structure to repo with sample test file | Research SQLAlchemy PostgreSQL
Code for login dialog window (frontend) added to view.py
Research Logging in Python

## Sanju
2019-11-04 | 2019-11-05 | 2019-11-06 | 2019-11-07 | 2019-11-08 | 2019-11-09 | 2019-11-10 | 2019-11-11 | 2019-11-12 | 2019-11-13 | 2019-11-14
[5 empty] | S A T U R D A Y | S U N D A Y
Learnt command prompt GIT commands
Downlaoded Postgresql

## Tamdin
2019-11-04 | 2019-11-05 | 2019-11-06 | 2019-11-07 | 2019-11-08 | 2019-11-09 | 2019-11-10 | 2019-11-11 | 2019-11-12 | 2019-11-13 | 2019-11-14
[5 empty] | S A T U R D A Y | S U N D A Y
Learnt command prompt GIT commands | learnt about building a GUI desktop calcultor using pyQt5 and python | learnt a bit about logging in python
Downlaoded Postgresql | learnt about pytest and unittest